**5/20-5/22**

Good to Great Week

**5/24 Draft 2**

Includes outcomes with assessments and action steps

**5/31 Feedback**

From Abby

**3/5 Directors’ Meeting**

Timeline

Common language

Strategic plan overview

**Mid-March**

AVPs share goals

**Late-March**

Letter from VP

**8/1 and Beyond**

Implementation of plan

Data in Campus Labs

Rewards for participation

Quarterly reminders

Linking DoSA plan to AU plan

**7/1 Final Draft**

**Mid-July**

Revisions and

preparation for publication

**6/4**

June Goal Summit

**6/19 Draft 3**

All pieces set

Minor revisions

**4/2 Directors’ Meeting**

SMART objectives and outcomes

Common language

**4/22 Draft 1**

Includes objectives

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **March** | **April** | **May** | **June** | **July** | **August** |

**6/3 - 7/31 Campus Labs Trainings**

**3/18 - 4/5 SMART Objectives and Outcomes Trainings**

**2013**

Items in Green = Amy’s specific dates Items in Blue = Kim’s specific dates

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| March | April | May | June | July | August |
| |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | S | M | T | W | T | F | S | |  |  |  |  |  | 1 | 2 | | 3 | 4 | 5 | 6 | 7 | 8 | 9 | | 10 | 11 | 12  Abby  Strategic. Plan  overview  w/ Kim’s  Team | 13 | 14 Campus Labs Leader  Webinar | 15 | 16 | | 17 | 18 | 19 | 20 | 21 | 22 | 23 | | 24 | 25 | 26  Abby  Strategic. Plan  Overview w/  Amy’s Team | 27 | 28 | 29  HW  Pre-draft  1 | 30 | | 31 |  |  |  |  |  |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | S | M | T | W | T | F | S | |  | 1 | 2  HW/w  Abby  Feed-back | 3  Abby  Objectives  w/  Amy’s  Team | 4 | 5 | 6 | | 7 | 8 | 9 | 10 | 11 | 12 | 13 | | 14 | 15  HW Final Draft 1 | 16 | 17 | 18 | 19 | 20 | | 21 | 22  **Draft**  **One** | 23  HW  Team  Outcomes&  Action Steps | 24 | 25 | 26 | 27 | | 28 | 29 | 30  HW  Pre-draft 2 |  |  |  |  | |  |  |  |  |  |  |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | S | M | T | W | T | F | S | |  |  |  | 1 | 2 | 3  HW/w  Abby  Feed-back  Draft 2 | 4 | | 5 | 6 | 7 | 8 | 9 | 10 | 11 | | 12 | 13  HW Final Draft 2 | 14  Abby  Outcomes  w/  Amy’s  Team | 15 | 16 | 17 | 18 | | 19 | 20  **Good** | 21  **to** | 22  **Great**  HW Team w/core  values&DoSA Strategic Plan | 23 | 24  **Draft**  **Two** | 25 | | 26 | 27 | 28 | 29 | 30 | 31  **Feed-**  **back** |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | S | M | T | W | T | F | S | |  |  |  |  |  |  | 1 | | 2 | 3  HW  Pre-draft  3 | 4  **Goal Summit** | 5 | 6 | 7 | 8 | | 9 | 10 | 11 | 12 | 13  Values Focus Group | 14  HW Final Draft 3 | 15 | | 16 | 17  Values Focus Group | 18 | 19  **Draft**  **Three**  Values Focus Group | 20 | 21 | 22 | | 23 | 24 | 25 | 26 | 27 | 28 | 29 | | 30 |  |  |  |  |  |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | S | M | T | W | T | F | S | |  | 1  **Final**  **Draft** | 2 | 3 | 4 | 5  Values survey closes | 6 | | 7 | 8 | 9 | 10  CA Training | 11 | 12 | 13 | | 14 | 15 | 16 | 17  CA Training | 18  CA Training | 19 | 20 | | 21 | 22 | 23  Baseline  Training | 24 | 25  Baseline  Training | 26 | 27 | | 28 | 29 | 30 | 31  Outcomes due in CA |  |  |  | |  |  |  |  |  |  |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | S | M | T | W | T | F | S | |  |  |  |  | 1 | 2 | 3 | | 4 | 5 | 6 | 7 | 8 | 9 | 10 | | 11 | 12 | 13 | 14 | 15 | 16 | 17 | | 18 | 19 | 20 | 21 | 22 | 23 | 24 | | 25 | 26 | 27 | 28 | 29 | 30 | 31 | |  |  |  |  |  |  |  | |